## WORK PLAN
WORK PLAN
INTRODUCTION | Over the past years, IT operation has remained steady but that it is not well-orgnanized and functionings. I would like to make it well-organized and be easier for staff and IT itself is stayed on track and clear focus. Staff have access and stayed in well-organized and documents safety. Once the system is well-organized and controlled that points would be able to help staff process their work faster, safely and with ease.
GOAL 1: | Maintenance the anti-Virus consistent
OBJECTIVES | TIMELINE | RESOURCES | RESPONSIBILITIES | STRATEGY
Set number of certain anti-viruses/purchase a new brand | 2022-03-14 | ED-Credit card | IT | - Review all existings anti-viruses - Set number of staff for use - Set number of anti-viruses for use - Check if it is expired and renewal - Deploy for users - if the current one is not capable to pretect our operating system well, so it needs to purchase another one instead
GOAL 2: | Maintenance the office365 license consistent
OBJECTIVES | TIMELINE | RESOURCES | RESPONSIBILITIES | STRATEGY
Set number of certain licenses/change annual plan | 2022-04-01 | ED-Credit card | IT | - Review all exisitng the licenses - set number of staff for use - set number of license for use - change the annual plan if needed
GOAL 3: | New server machine
OBJECTIVES | TIMELINE | RESOURCES | RESPONSIBILITIES | STRATEGY
Setup a new server machine | 2022-05-01 | 7000 | IT | - Study a kind of server machine model - Find three quotes to compare qualifications - Setup a new operating system - Configure a server machine to a DC controller - Organize GPO categories to deploy - Organize staff to join this server machine Note: Backup the configuration from current to integrate a new one setup
GOAL 4: | Database
OBJECTIVES | TIMELINE | RESOURCES | RESPONSIBILITIES | STRATEGY
Develop a new database system | 2022-10-01 | Monitor + Software Tool Licensing | IT | - Determine the purpose of database - Find and organize the information required - Devide the information into tables - Turn information items into columns - Specify primary keys - Set the table relationships -Refine the design -Apply the normalization rules -Analysis about system behaviour -Starting a structure of system -Implement for layout - Coding

## WEEK 3-MARCH
WORK PLAN
Week 3 in March
Monday | Tuesday | Wednesday | Thursday | Friday
Check anti-virus on purchase invoice with finance team & the Norton website | An appointment to see Dr - Lip & Ear; 9am | Check office365 on purcahse invoice history | Review Server + Printer | Review Printer + Domain
Count a number of staff for use | Process to set a certain of anti-virus + Credit Card | Count a number of staff for use | Scan to folder for all in Server Machine | Scan to email
Set number of anti-virus for use | Two laptops will be arrived and sign on documents - Orignal tax invoice, Original delivery note and Officail receipt. | Set number of office365 license for use annually plan & change the plan if needed | Set users for scan to folder for each/all | Set user to scan to eamil for each
Check the anti-viruse for expiry date |  |  | Translate Use of Resources of gadc property to Khmer version
Mey - Cannot print pdf file to printer and printer itself still shows the last paper |  |  | Translate use of technology to Khmer version
Have a meeting with Siven about working progress; 2pm-2.30pm - Postpone to Wendesday 16th March

## WEEK 4-MARCH
WORK PLAN
Week 4 in March + 4falling days
Monday | Tuesday | Wednesday | Thursday | Friday
2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25
- Had the meeting with Lina about asset update - Delayed - Prepared the asset list for betting - Have a meeting with Siven-Delayed | - Check the asset list again for betting - prepare Timesheet of as in Marh-22 & also -re-organize the January timesheet to replace the previous one which is missed to put Compensation Earned | - Organize the Cash Advance Request Form to replace Hard Drive for Prak Chanposda's laptop - 1TB | - Update asset list on new products which has two laptops & accessories - Check the office365 subscription plan- Monthly | - Submit the re-imburement of ED credit card - charged for 16qty - Submit the Cash Advance to Finance team - delayed Bong Lina's working from home
28-Mar-22 | 29-mar-22 | 30-mar-22 | 31-mar-22 | 01-Apr-22
- Carrying on to heck office365 and email to inform Bong Lina and change the plan - Have a meeting with Siven - Re-structure page (What we do, Advocacy and Networking, Community Outreach, Capacity Development, GADNet, Cambodia Man Network - CMN, Committee to promote Woman in politics - CPWP). - Update Job relate page and news&events related. | - Install anti-virus to staff | - Install anti-virus to staff | - Staff meeting ( Monks blessing, and Meal solidarity) - New document Forms - present by me | - Confirm from Bong Lina then then Purchase Windows server license and activate it - Check the current and clear configurations on Server Machine -Change Office365 plan

## WEEK 1-APRIL
WORK PLAN
Week 1 in April
Monday | Tuesday | Wednesday | Thursday | Friday
2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08
- Have a meeting with Siven about her progress Delayed to Friday She traling to Kratie and K.Cham - Follow up Bong Lina about to purchase a server license - Develop a video to check computer name to share to staff - developed the guide document already -Prepare the property document sign for all staff | - Send the video guide to ask staff to check their computer name - already sent the guide document to ask them to check it -Waiting for bong Lina reply to change the office 365 plan & Window server license purchasing -Prepare the property document sign for all staff | - Asking each staff to sign on property holding form | - Asking each staff to sign on property holding form | - prepare my laptop to replace Sopeak Pech

## WEEK 3-APRIL
WORK PLAN
Week 3 in April
Monday | Tuesday | Wednesday | Thursday | Friday
2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22
-Working on website - layout adjustment and content writing - Having a meeting with Siven | -Working on website - continue -prepare a laptop bong Lina for Roth replacement -Prepare a laptop for Pech Sopheak remplacement | -Working on website - continue -Continue to asking staff sign on a doc for property and technology&software | -Working on website - continue | -Working on website - continue